## Timeline
Capital campaign timeline
Campaign start | 2027-03-01 | Change this one cell. Every phase's Start and End date below follows it.
Phase | Start | End | Gate | Target share of goal | Owner
Readiness |  |  | Readiness checklist tab scores at least seventeen of twenty. | 0 percent | Executive director and board chair
Feasibility study |  |  | Interviews complete. Case and goal confirmed or revised, or skipped only if leadership donors have already committed half the goal. | 0 percent, or 50 percent if the study is skipped | Board, through outside counsel
Quiet phase |  |  | Leadership and major gifts solicited one at a time, face to face. | About 90 percent | Development lead, with the executive director on top prospects
Public phase |  |  | The campaign is announced and the wider donor file is asked. | 100 percent, the final share from most of the donor count | Development lead and communications
Close |  |  | Pledges collected on schedule. The project or endowment is funded. | 100 percent, tracked to the pledge | Finance lead, with the board treasurer
Phase lengths are typical, not fixed: six weeks for readiness, ten for the feasibility study, a year for the quiet phase, six months for the public phase, and four years for pledge collection at close. A campaign well outside the $4M to $9M range will run longer or shorter at every phase.
Do not move a phase's End date earlier than planned because a calendar date arrived. Move it when the gate and the target share are met.
Capital campaign timeline
Read the guide: nonprofitstrategy.org/capital-campaign-feasibility-study/
Note on A4: Five phases in order. Do not open a phase before the gate on the one before it is met.
Note on B4: The first phase starts on the Campaign start cell above. Every phase after it starts when the one before it ends.
Note on C4: Start plus the typical length for this phase, described in the guide. Typical, not fixed. Adjust for your own campaign size.
Note on D4: What has to be true before the next phase opens.
Note on E4: How much of the goal should be committed by the end of this phase, from the guide's own figures.
Note on F4: The one person accountable for the gate, not a committee.

## Gift range chart
Gift range chart
Campaign goal | 4000000 | Change this one cell. Every tier below recalculates from it.
Lead gift as percent of goal | 10% | AFP's own readiness check asks for at least 10 percent. Some counsel look for closer to a fifth on a first campaign.
Prospects needed per gift | 4 | A common planning ratio. Raise it if your prospect list is thin.
Tier | Gift size | Gifts needed | Prospects needed | Tier total | Running total
1 |  | 1
2
3
4
5
6
7
8
Eight tiers at a constant total per tier cover roughly eight times the lead gift's share of the goal. The remainder comes from the broader donor file in the public phase, at a far lower dollar per donor. Add tiers below the eighth if your prospect base needs them.
Capital campaign timeline
Read the guide: nonprofitstrategy.org/capital-campaign-feasibility-study/
Note on A6: Tier one is the lead gift. Each tier below it is roughly half the size of the one above.
Note on B6: Tier one is the goal times the lead gift percentage above. Every tier after it is half the tier above.
Note on C6: Doubles each tier down, so every tier raises roughly the same total as tier one.
Note on D6: Gifts needed times the prospect ratio above. Real campaigns lose most prospects between naming and closing.
Note on E6: Gift size times gifts needed.
Note on F6: This tier's total plus every tier above it.

## Readiness checklist
Readiness checklist
Mark each item Yes or No from the dropdown. The score below totals the Yes answers out of twenty.
Group | Item | Answer
Board | Every board member has made or pledged a personal campaign gift.
Board | The board has passed a resolution approving the goal and the case.
Board | At least three board members are ready to serve on the campaign cabinet.
Board | The board chair has confirmed the board's giving is at 100 percent.
Donors | A lead prospect capable of giving near a tenth of the goal is named.
Donors | The next 100 donors by lifetime giving are listed and current.
Donors | At least ten prospects for the top three gift tiers are named.
Donors | No single funder or donor is an unmanaged concentration risk.
Staff | A development lead with campaign experience is on staff or contracted.
Staff | The executive director's campaign time is budgeted, not layered on.
Staff | Administrative and data support is in place for pledge tracking.
Staff | Staff capacity exists to run the campaign without abandoning the annual fund.
Case | The case names the specific outcome the money buys, not the building.
Case | The case has been tested with board members and key donors.
Case | Named giving opportunities are mapped to specific project components.
Case | The case ties directly to the current strategic plan.
Systems | The donor database can produce a clean top 100 list in an afternoon.
Systems | Gift acceptance policy covers multi year pledges and noncash gifts.
Systems | The pledge system can track multi year payment schedules and reminders.
Systems | Three consecutive years of financial statements are clean and current.
Score
Reading
Capital campaign timeline
Read the guide: nonprofitstrategy.org/capital-campaign-feasibility-study/
Note on A4: One of five areas: board, donors, staff, case, or systems.
Note on B4: A specific, checkable fact, not an opinion.
Note on C4: Yes or No, from the dropdown.